## Sheet1
Phase | Task Name | Resource | Start | Duration | Milestone | %Completion | Dept Responsible | Cost
Phase 1 | Scope | Project Manager | 2020-07-02 | 4 |  | 60 | Customer | 500
Phase 1 | Analysis | Analyst | 2020-07-07 | 5 |  | 85 | In house | 1500
Phase 1 | Software Requirements | Analyst | 2020-07-12 | 10 |  | 37 | Customer | 200
Phase 1 | Design | Architect | 2020-07-25 | 5 |  | 31 | In house | 3000
Phase 2 | Development | Developer | 2020-08-05 | 31 |  | 55 | In house | 1600
Phase 2 | Development | Developer | 2020-08-25 | 1 | Wireframe |  | In house
Phase 2 | Development | Developer | 2020-09-01 | 1 | Prototype |  | In house
Phase 2 | Functional testing | Test | 2020-08-15 | 15 |  | 88 | In house | 2000
Phase 2 | E2E Testing | Test | 2020-08-27 | 10 |  | 0 | In house | 2500
Phase 2 | Stablization | Developer | 2020-09-01 | 7 |  | 0 | In house | 2000
Phase 3 | Training | Tech Communicator | 2020-09-15 | 10 |  | 0 | In house | 2000
Phase 3 | Documentation | Tech Communicator | 2020-09-02 | 10 |  | 0 | In house | 2000
Phase 3 | Pilot | Project Manager | 2020-09-25 | 15 |  | 0 | Customer | 2000
Phase 3 | Deployment | Operations | 2020-10-01 | 5 |  | 0 | Customer | 2000
Phase 3 | Post Implementation Review | Project Manager | 2020-10-10 | 3 |  | 0 | Customer | 2000